## Daily Reports
Daily Report Bách - 01/10/2026 đến 19/10/2026
Mỗi ngày gồm nhiều dòng công việc theo mẫu Task / Details / Backlog ID / Duration / Progress. Ngày không có commit được phân bổ tiến độ theo yêu cầu người dùng.
Số ngày | 19 | Dòng công việc | 62 | Tổng thời lượng | 133 | Ngày phân bổ tiến độ | 12
Report Date | Day | Task | Details | Backlog ID | Duration Hours | Progress | Delay / Issues | Git Repository | Git References | Git URLs | Source | Backlog Comment | Posted Issue Key
2026-10-01T00:00:00.000Z | Thứ Năm | [BE] | Work day và reconcile queue cho chấm công | — | 2 | 100% | Nothing | human-resource-management | d9040fe5, 7d0d770c, 5d62becb, 29415b04, 1eadc723, 6336c1f0, 0a2d968c; MR !89, !90, !91, !94, !95 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/d9040fe5a9309536026b89158742461bd4a26d3c | Git local
2026-10-01T00:00:00.000Z | Thứ Năm | [BE] | Xử lý IN/OUT, session, work day và endpoint process | — | 2 | 100% | Nothing | human-resource-management | d9040fe5, 7d0d770c, 5d62becb, 29415b04, 1eadc723, 6336c1f0, 0a2d968c; MR !89, !90, !91, !94, !95 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/d9040fe5a9309536026b89158742461bd4a26d3c | Git local
2026-10-01T00:00:00.000Z | Thứ Năm | [BE] | GET /v1/hrm/attendance/me/today | — | 1.5 | 100% | Nothing | human-resource-management | d9040fe5, 7d0d770c, 5d62becb, 29415b04, 1eadc723, 6336c1f0, 0a2d968c; MR !89, !90, !91, !94, !95 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/d9040fe5a9309536026b89158742461bd4a26d3c | Git local
2026-10-01T00:00:00.000Z | Thứ Năm | [FE] | Today card và đồng bộ trang lịch sử chấm công | — | 1 | 100% | Nothing | human-resource-management | d9040fe5, 7d0d770c, 5d62becb, 29415b04, 1eadc723, 6336c1f0, 0a2d968c; MR !89, !90, !91, !94, !95 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/d9040fe5a9309536026b89158742461bd4a26d3c | Git local
2026-10-01T00:00:00.000Z | Thứ Năm | [docs] | Cập nhật spec, decision record và runbook | — | 0.5 | 100% | Nothing | human-resource-management | d9040fe5, 7d0d770c, 5d62becb, 29415b04, 1eadc723, 6336c1f0, 0a2d968c; MR !89, !90, !91, !94, !95 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/d9040fe5a9309536026b89158742461bd4a26d3c | Git local
2026-10-02T00:00:00.000Z | Thứ Sáu | [analysis] | Phân tích scope, filter và export của UC-3.9 | — | 2 | 20% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-02T00:00:00.000Z | Thứ Sáu | [BE] | Thiết kế company context và truy vấn headcount | — | 3 | 25% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-02T00:00:00.000Z | Thứ Sáu | [FE] | Thiết kế data contract và filter model | — | 2 | 15% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-03T00:00:00.000Z | Thứ Bảy | [BE] | Xây dựng GET báo cáo headcount | — | 3 | 60% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-03T00:00:00.000Z | Thứ Bảy | [BE] | Xây dựng export Excel/PDF | — | 2 | 45% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-03T00:00:00.000Z | Thứ Bảy | [FE] | Xây dựng data layer, filter và i18n | — | 2 | 35% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-04T00:00:00.000Z | Chủ Nhật | [BE] | Hoàn thiện API danh sách và export headcount | — | 2 | 85% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-04T00:00:00.000Z | Chủ Nhật | [FE] | Hoàn thiện report page, table và export UI | — | 3 | 70% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-04T00:00:00.000Z | Chủ Nhật | [test] | Kiểm tra filter, export và RBAC | — | 2 | 60% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-05T00:00:00.000Z | Thứ Hai | [BE] | Hoàn thành headcount list và export | — | 2 | 100% | Nothing | human-resource-management | 0c565f7a, 4a5207ef, 3daedda5, c51e2f27, bed6b3b0, f9a7f17b, 121d8d93; MR !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/0c565f7a865e68068cb5eff467bb1adb4410b833 | Git local
2026-10-05T00:00:00.000Z | Thứ Hai | [FE] | Hoàn thành data layer, filter và report page | — | 3 | 100% | Nothing | human-resource-management | 0c565f7a, 4a5207ef, 3daedda5, c51e2f27, bed6b3b0, f9a7f17b, 121d8d93; MR !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/0c565f7a865e68068cb5eff467bb1adb4410b833 | Git local
2026-10-05T00:00:00.000Z | Thứ Hai | [FE] | Hoàn thành route, sidebar và RBAC | — | 1 | 100% | Nothing | human-resource-management | 0c565f7a, 4a5207ef, 3daedda5, c51e2f27, bed6b3b0, f9a7f17b, 121d8d93; MR !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/0c565f7a865e68068cb5eff467bb1adb4410b833 | Git local
2026-10-05T00:00:00.000Z | Thứ Hai | [docs] | Chốt spec và decision record UC-3.9 | — | 1 | 100% | Nothing | human-resource-management | 0c565f7a, 4a5207ef, 3daedda5, c51e2f27, bed6b3b0, f9a7f17b, 121d8d93; MR !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/0c565f7a865e68068cb5eff467bb1adb4410b833 | Git local
2026-10-06T00:00:00.000Z | Thứ Ba | [integration] | Đồng bộ develop và xử lý merge UC-3.9 | — | 3 | 100% | Nothing | human-resource-management | 0491ed4b, 5e504418; MR !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/0491ed4b91da7708128b425a4b3dcdf30d9de75d | Git local
2026-10-06T00:00:00.000Z | Thứ Ba | [test] | Kiểm tra UC-3.9 sau merge | — | 2 | 100% | Nothing | human-resource-management | 0491ed4b, 5e504418; MR !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/0491ed4b91da7708128b425a4b3dcdf30d9de75d | Git local
2026-10-06T00:00:00.000Z | Thứ Ba | [analysis] | Phân tích scope và data model UC-4.14 | — | 2 | 20% | Nothing | human-resource-management | 0491ed4b, 5e504418; MR !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/0491ed4b91da7708128b425a4b3dcdf30d9de75d | Git local
2026-10-07T00:00:00.000Z | Thứ Tư | [DB] | Thiết kế schema và migration project phase | — | 2 | 60% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-07T00:00:00.000Z | Thứ Tư | [BE] | Xây dựng phase CRUD, list và soft delete | — | 3 | 45% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-07T00:00:00.000Z | Thứ Tư | [FE] | Xây dựng luồng Gantt/list CRUD | — | 2 | 35% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-08T00:00:00.000Z | Thứ Năm | [DB] | Hoàn thành schema project phase | — | 1 | 100% | Nothing | human-resource-management | 28426ced, eb26c741, 954da9c5, 596be210, dd5fcf92, 37837901, 75749967; MR !117, !118 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/28426ced7ae830621764467bf075e9becc9ae88b | Git local
2026-10-08T00:00:00.000Z | Thứ Năm | [BE] | Hoàn thành API quản lý project phase | — | 2 | 100% | Nothing | human-resource-management | 28426ced, eb26c741, 954da9c5, 596be210, dd5fcf92, 37837901, 75749967; MR !117, !118 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/28426ced7ae830621764467bf075e9becc9ae88b | Git local
2026-10-08T00:00:00.000Z | Thứ Năm | [FE] | Hoàn thành Gantt/list CRUD project phase | — | 3 | 100% | Nothing | human-resource-management | 28426ced, eb26c741, 954da9c5, 596be210, dd5fcf92, 37837901, 75749967; MR !117, !118 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/28426ced7ae830621764467bf075e9becc9ae88b | Git local
2026-10-08T00:00:00.000Z | Thứ Năm | [docs/style] | Cập nhật spec/RBAC và đồng bộ division layout | — | 1 | 100% | Nothing | human-resource-management | 28426ced, eb26c741, 954da9c5, 596be210, dd5fcf92, 37837901, 75749967; MR !117, !118 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/28426ced7ae830621764467bf075e9becc9ae88b | Git local
2026-10-09T00:00:00.000Z | Thứ Sáu | [retro] | Lập inventory module và MR đã hoàn thành | — | 3 | 20% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-09T00:00:00.000Z | Thứ Sáu | [review] | Rà soát kiến trúc và domain boundaries | — | 2 | 15% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-09T00:00:00.000Z | Thứ Sáu | [handover] | Thu thập source, spec và runbook bàn giao | — | 2 | 15% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-10T00:00:00.000Z | Thứ Bảy | [retro] | Review attendance và facelog | — | 3 | 40% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-10T00:00:00.000Z | Thứ Bảy | [retro] | Review division và project management | — | 2 | 35% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-10T00:00:00.000Z | Thứ Bảy | [handover] | Lập status matrix theo module | — | 2 | 30% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-11T00:00:00.000Z | Chủ Nhật | [review] | Audit technical debt và rủi ro | — | 3 | 55% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-11T00:00:00.000Z | Chủ Nhật | [docs] | Đối chiếu spec, decision record và runbook | — | 2 | 50% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-11T00:00:00.000Z | Chủ Nhật | [handover] | Tổng hợp environment, branch và vận hành | — | 2 | 45% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-12T00:00:00.000Z | Thứ Hai | [retro] | Tổng hợp open items, dependency và risk | — | 3 | 70% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-12T00:00:00.000Z | Thứ Hai | [handover] | Tổng hợp module ownership và integration points | — | 2 | 60% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-12T00:00:00.000Z | Thứ Hai | [handover] | Soạn transition plan | — | 2 | 60% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-13T00:00:00.000Z | Thứ Ba | [retro] | Chốt lessons learned và technical debt | — | 3 | 90% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-13T00:00:00.000Z | Thứ Ba | [handover] | Hoàn thiện status và priority backlog | — | 2 | 85% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-13T00:00:00.000Z | Thứ Ba | [handover] | Chuẩn bị walkthrough và FAQ | — | 2 | 80% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-14T00:00:00.000Z | Thứ Tư | [retro] | Retro toàn bộ dự án | — | 3 | 100% | Nothing |  | Thông tin do người dùng cung cấp |  | User-provided
2026-10-14T00:00:00.000Z | Thứ Tư | [handover] | Walkthrough dự án cho lead mới | — | 3 | 100% | Nothing |  | Thông tin do người dùng cung cấp |  | User-provided
2026-10-14T00:00:00.000Z | Thứ Tư | [handover] | Chốt Q&A, action và risk sau bàn giao | — | 1 | 100% | Nothing |  | Thông tin do người dùng cung cấp |  | User-provided
2026-10-15T00:00:00.000Z | Thứ Năm | [audit] | Audit màn hình và luồng hợp đồng FE-05 | HRM-387 | 3 | 25% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-15T00:00:00.000Z | Thứ Năm | [fix] | Rà lỗi nhóm loại hợp đồng và catalog order | HRM-377, HRM-378 | 2 | 20% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-15T00:00:00.000Z | Thứ Năm | [analysis] | Phân tích expiry, renewal và contract file | HRM-383, HRM-384 | 2 | 15% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-16T00:00:00.000Z | Thứ Sáu | [BE] | Sửa API group/order của contract type | HRM-377 | 3 | 60% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-16T00:00:00.000Z | Thứ Sáu | [FE] | Sửa contract screen và dropdown | HRM-378, HRM-387 | 2 | 55% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-16T00:00:00.000Z | Thứ Sáu | [test] | Kiểm tra permission và renewal cases | HRM-383, HRM-384 | 2 | 40% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-17T00:00:00.000Z | Thứ Bảy | [BE] | Xử lý expiration, renewal validation và file persistence | HRM-383 | 3 | 80% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-17T00:00:00.000Z | Thứ Bảy | [FE] | Xử lý upload, late renewal và type selection | HRM-384 | 3 | 80% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-17T00:00:00.000Z | Thứ Bảy | [docs/test] | Kiểm tra boundary/security và cập nhật UC-5.2 | HRM-382 | 1 | 70% | Nothing | human-resource-management |  |  | Progress allocation (user-requested)
2026-10-18T00:00:00.000Z | Chủ Nhật | [fix] | Hoàn thành type group, catalog và contract screen fixes | HRM-377, HRM-378, HRM-387 | 2 | 100% | Nothing | human-resource-management | dd0258f1, b374db6d, ca6130b3, 30f5f1a5, bf2df704, 15eb6822 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/dd0258f1a043079baaf9dc9185dfd8dd4423f0cb | Git local
2026-10-18T00:00:00.000Z | Chủ Nhật | [BE] | Hoàn thành expiry, renewal validation và file store | HRM-383, HRM-386 | 2 | 100% | Nothing | human-resource-management | dd0258f1, b374db6d, ca6130b3, 30f5f1a5, bf2df704, 15eb6822 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/dd0258f1a043079baaf9dc9185dfd8dd4423f0cb | Git local
2026-10-18T00:00:00.000Z | Chủ Nhật | [FE] | Hoàn thành upload và renewal UI | HRM-384 | 2 | 100% | Nothing | human-resource-management | dd0258f1, b374db6d, ca6130b3, 30f5f1a5, bf2df704, 15eb6822 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/dd0258f1a043079baaf9dc9185dfd8dd4423f0cb | Git local
2026-10-18T00:00:00.000Z | Chủ Nhật | [docs] | Đồng bộ contract spec | HRM-382, HRM-385 | 1 | 100% | Nothing | human-resource-management | dd0258f1, b374db6d, ca6130b3, 30f5f1a5, bf2df704, 15eb6822 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/dd0258f1a043079baaf9dc9185dfd8dd4423f0cb | Git local
2026-10-19T00:00:00.000Z | Thứ Hai | [tooling] | Hoàn thiện Sprint 6 importer, check, dry-run và state | — | 3 | 100% | Nothing | backlog-bulldozer | 5321fe3, f36d417 | https://github.com/stillthethrone/backlog-bulldozer/commit/5321fe391688629076d2895ba57f7ecd32493514 | Git local
2026-10-19T00:00:00.000Z | Thứ Hai | [data] | Tạo Daily Report workbook và ánh xạ nguồn | HRM-319 | 3 | 100% | Nothing | backlog-bulldozer | 5321fe3, f36d417 | https://github.com/stillthethrone/backlog-bulldozer/commit/5321fe391688629076d2895ba57f7ecd32493514 | Git local
2026-10-19T00:00:00.000Z | Thứ Hai | [docs] | Cập nhật hướng dẫn và kiểm tra hồi quy | HRM-319 | 1 | 100% | Nothing | backlog-bulldozer | 5321fe3, f36d417 | https://github.com/stillthethrone/backlog-bulldozer/commit/5321fe391688629076d2895ba57f7ecd32493514 | Git local

## Backlog Setup
Backlog issue setup
Daily Report là trạng thái; Issue Type vẫn là Task. Existing Issue Key giúp tránh tạo trùng issue tháng.
Project | Summary | Issue Type | Status | Priority | Assignee | Category | Milestone | Version | Start Date | Due Date | Estimated Hours | Actual Hours | Resolution | Existing Issue Key
HRM | [Daily Report] Bách 10/2026 | Task | Daily Report | Normal | Duong Tung Bach |  | sprint #6 | sprint #6 | 2026-10-01T00:00:00.000Z | 2026-10-31T00:00:00.000Z |  |  |  | HRM-319

## Git Activity
Git activity sources
Nguồn: lịch sử Git local và các MR hiển thị trong ảnh người dùng cung cấp.
Commit Date | Repository | Commit | Author | Subject | Related MR | URL | Source Type
2026-10-01T00:00:00.000Z | human-resource-management | d9040fe5a9309536026b89158742461bd4a26d3c | Duong Tung Bach | feat(uc-8.1): store processed work days and a reconcile queue | !94 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/d9040fe5a9309536026b89158742461bd4a26d3c | Commit
2026-10-01T00:00:00.000Z | human-resource-management | 7d0d770cfa2642a3c5736e34fe5befd2c58e6335 | Duong Tung Bach | feat(uc-8.1): resolve punches into IN/OUT, sessions and work days | !94 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/7d0d770cfa2642a3c5736e34fe5befd2c58e6335 | Commit
2026-10-01T00:00:00.000Z | human-resource-management | 5d62becb51ff5729643495ad03781f8ad7f64f43 | Duong Tung Bach | feat(uc-8.1): process work days from a durable queue and add POST /attendance/events/process | !94 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/5d62becb51ff5729643495ad03781f8ad7f64f43 | Commit
2026-10-01T00:00:00.000Z | human-resource-management | 29415b046a09da847569b0f3190d54fecd09f2e1 | Duong Tung Bach | docs(uc-8.1): spec updates, decision record and runbook for attendance processing | !94 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/29415b046a09da847569b0f3190d54fecd09f2e1 | Commit
2026-10-01T00:00:00.000Z | human-resource-management | 1eadc723a3bbb916ea99ea2cbefccfb6f80089a1 | Duong Tung Bach | feat(uc-8.1): add GET /v1/hrm/attendance/me/today and align history with processed days | !95 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/1eadc723a3bbb916ea99ea2cbefccfb6f80089a1 | Commit
2026-10-01T00:00:00.000Z | human-resource-management | 6336c1f0c385f632a604d0df259af3ebaec80e21 | Duong Tung Bach | feat(uc-8.1): show today's attendance on the history page | !95 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/6336c1f0c385f632a604d0df259af3ebaec80e21 | Commit
2026-10-01T00:00:00.000Z | human-resource-management | 0a2d968caf7d8f1bdc6e209470853398d397594e | Duong Tung Bach | docs(uc-8.1): spec updates and decision record for me/today and the history alignment | !95 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/0a2d968caf7d8f1bdc6e209470853398d397594e | Commit
2026-10-01T00:00:00.000Z | human-resource-management | a51b08ae418566e3b3714ad432fbecde9384c039 | Trần Ngọc Thắng | Merge branch 'fix/TECH-8.2-review' into 'develop' | !90 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/a51b08ae418566e3b3714ad432fbecde9384c039 | MR merge
2026-10-01T00:00:00.000Z | human-resource-management | ff8ae04a64117eb626bfea7238141e4d194bb4be | Trần Ngọc Thắng | Merge branch 'feat/TECH-8.1-device-registry' into 'develop' | !91 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/ff8ae04a64117eb626bfea7238141e4d194bb4be | MR merge
2026-10-01T00:00:00.000Z | human-resource-management | c149b213b949197f6f8bfd8bce1c8e25c5b887de | Trần Ngọc Thắng | Merge branch 'feat/TECH-8.1.4-mqtt-auth' into 'develop' | !89 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/c149b213b949197f6f8bfd8bce1c8e25c5b887de | MR merge
2026-10-05T00:00:00.000Z | human-resource-management | 0c565f7a865e68068cb5eff467bb1adb4410b833 | Duong Tung Bach | refactor(api): extract company-context resolution from DivisionService | !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/0c565f7a865e68068cb5eff467bb1adb4410b833 | Commit
2026-10-05T00:00:00.000Z | human-resource-management | 4a5207ef48ce2578e47717df7c6f82e32551195d | Duong Tung Bach | feat(api): add GET /reports/divisions/headcount for the staff scale report (UC-3.9) | !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/4a5207ef48ce2578e47717df7c6f82e32551195d | Commit
2026-10-05T00:00:00.000Z | human-resource-management | 3daedda5d534da5562b11853f37aad5caf4ce8f3 | Duong Tung Bach | feat(api): add GET /reports/divisions/headcount/export to download the report as Excel or PDF (UC-3.9) | !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/3daedda5d534da5562b11853f37aad5caf4ce8f3 | Commit
2026-10-05T00:00:00.000Z | human-resource-management | c51e2f27011436f94e5963b79dcaededbd16a079 | Duong Tung Bach | feat(web): add data layer, filter rules and i18n for the division headcount report (UC-3.9) | !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/c51e2f27011436f94e5963b79dcaededbd16a079 | Commit
2026-10-05T00:00:00.000Z | human-resource-management | bed6b3b0e2a2fbff7d1ebe631e552593de9f094a | Duong Tung Bach | feat(web): add the division headcount report page with filters, table and Excel/PDF export (UC-3.9) | !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/bed6b3b0e2a2fbff7d1ebe631e552593de9f094a | Commit
2026-10-05T00:00:00.000Z | human-resource-management | f9a7f17b7e76c7c3f902f907ad983ce8940eca43 | Duong Tung Bach | feat(web): route and sidebar entry for the division headcount report, HR Manager and BOM only (UC-3.9) | !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/f9a7f17b7e76c7c3f902f907ad983ce8940eca43 | Commit
2026-10-05T00:00:00.000Z | human-resource-management | 121d8d93b464c2e9e3cf4f55833ccb9047be456d | Duong Tung Bach | docs(spec): record UC-3.9 headcount report in 03-division spec update and decisions | !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/121d8d93b464c2e9e3cf4f55833ccb9047be456d | Commit
2026-10-06T00:00:00.000Z | human-resource-management | 0491ed4b91da7708128b425a4b3dcdf30d9de75d | Duong Tung Bach | Merge remote-tracking branch 'origin/develop' into feature/hrm-division-headcount-report | !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/0491ed4b91da7708128b425a4b3dcdf30d9de75d | Commit
2026-10-06T00:00:00.000Z | human-resource-management | 5e5044186488150a29259e9aeea2695d4b857452 | Trần Ngọc Thắng | Merge branch 'feature/hrm-division-headcount-report' into 'develop' | !105 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/5e5044186488150a29259e9aeea2695d4b857452 | MR merge
2026-10-08T00:00:00.000Z | human-resource-management | 28426ced7ae830621764467bf075e9becc9ae88b | Duong Tung Bach | feat(db): add project phase code, acceptance objective, soft delete and planned status (UC-4.14) | !117 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/28426ced7ae830621764467bf075e9becc9ae88b | Commit
2026-10-08T00:00:00.000Z | human-resource-management | eb26c741a818c840961c0762bdc316893b2e8643 | Duong Tung Bach | feat(api): project phase management — list, create, update, soft delete (UC-4.14) | !117 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/eb26c741a818c840961c0762bdc316893b2e8643 | Commit
2026-10-08T00:00:00.000Z | human-resource-management | 954da9c5c20d75d8a3a7748b539f487432cbc6d9 | Duong Tung Bach | feat(web): project phases on the overview tab — Gantt/list, add, edit, delete (UC-4.14) | !117 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/954da9c5c20d75d8a3a7748b539f487432cbc6d9 | Commit
2026-10-08T00:00:00.000Z | human-resource-management | 596be210735302832924386360a83f6e643b69f7 | Duong Tung Bach | docs(spec): record UC-4.14 project phase management in 04-project and rbac spec updates | !117 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/596be210735302832924386360a83f6e643b69f7 | Commit
2026-10-08T00:00:00.000Z | human-resource-management | dd5fcf9246366697873120d181a04a3c4afaf444 | Duong Tung Bach | style(web): align division dissolution, transfer and headcount report pages with the division structure layout | !118 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/dd5fcf9246366697873120d181a04a3c4afaf444 | Commit
2026-10-08T00:00:00.000Z | human-resource-management | 3783790122658317eb600438f9be2d6246ce7c63 | Trần Ngọc Thắng | Merge branch 'feature/hrm-project-phase-management' into 'develop' | !117 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/3783790122658317eb600438f9be2d6246ce7c63 | MR merge
2026-10-08T00:00:00.000Z | human-resource-management | 75749967a9dd951cb24a6637bc279f3bf3794c7c | Trần Ngọc Thắng | Merge branch 'feature/hrm-division-headcount-report' into 'develop' | !118 | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/75749967a9dd951cb24a6637bc279f3bf3794c7c | MR merge
2026-10-18T00:00:00.000Z | human-resource-management | dd0258f1a043079baaf9dc9185dfd8dd4423f0cb | Duong Tung Bach | fix(contract): return contract type group and catalog order to the contract form |  | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/dd0258f1a043079baaf9dc9185dfd8dd4423f0cb | Commit
2026-10-18T00:00:00.000Z | human-resource-management | b374db6d317982b1549a76417001568074be9753 | Duong Tung Bach | fix(web): fix contract screen bugs found in the FE-05 audit |  | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/b374db6d317982b1549a76417001568074be9753 | Commit
2026-10-18T00:00:00.000Z | human-resource-management | ca6130b3e45f1fb0b1e9e3874824dab8dc910548 | Duong Tung Bach | docs(spec): record FE-05 contract fixes for 05-contract spec sync |  | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/ca6130b3e45f1fb0b1e9e3874824dab8dc910548 | Commit
2026-10-18T00:00:00.000Z | human-resource-management | 30f5f1a588be0e8b6416e30ca373c7e42a9b87b6 | Duong Tung Bach | feat(contract): expire lapsed contracts, validate renewal sources and store contract files |  | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/30f5f1a588be0e8b6416e30ca373c7e42a9b87b6 | Commit
2026-10-18T00:00:00.000Z | human-resource-management | bf2df704a147d226fdab88ff89eca611b1c7d886 | Duong Tung Bach | feat(web): contract file uploads, late renewal and contract type choice on renewal |  | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/bf2df704a147d226fdab88ff89eca611b1c7d886 | Commit
2026-10-18T00:00:00.000Z | human-resource-management | 15eb682244be2106f7e63dac09297b1524b44442 | Duong Tung Bach | docs(spec): record FE-05 expiry, renewal, contract file and tenant default changes |  | https://git.d-soft.com.vn/dng.pj0024.dsoft.management.tool/human-resource-management/-/commit/15eb682244be2106f7e63dac09297b1524b44442 | Commit
2026-10-19T00:00:00.000Z | backlog-bulldozer | 5321fe391688629076d2895ba57f7ecd32493514 | Duong Tung Bach | feat: support Sprint 6 workbook imports |  | https://github.com/stillthethrone/backlog-bulldozer/commit/5321fe391688629076d2895ba57f7ecd32493514 | Commit